## 202508958
NLP Project Preference Document |  |  |  | IT9002
Mentor : Sini Raj Pulari
Project Name:
Student Name: | Fatema Husain Hasan |  |  | Student I ID: 202508958
NLP Project Log File
Date | Week No | Task Name | Work done During the week (Bullet points /Description) | Issues Experienced if any
17th October 2025 | 4 | Exploring Recommended Topics | • Explored suggested NLP project areas. • Identified possible directions for the final project. | None
23rd October 2025 | 5 | Project Initiation & Data Selection | • Selected initial project idea. • Searched for datasets from Kaggle/UCI/etc. • Downloaded dataset samples and checked basic structure. | Some datasets were unstructured or required heavy cleaning.
31st October 2025 | 6 | Literature Review | • Reviewed existing research papers related to the chosen topic. • Identified gaps to address in the project. | Limited access to some academic sources.
7th November 2025 | 7 | Text Preprocessing | • Started cleaning text data (removing stopwords, punctuation). • Applied tokenization and simple preprocessing steps. | Some text entries required manual correction.
14th November 2025 | 8 | Text Representation Techniques | • Implemented text representation methods • Explored N-grams to capture contextual information. • Applied POS tagging and Named Entity Recognition using NLP libraries. | Feature dimensionality increased significantly for some representations.
21st November 2025 | 9 | Model Selection & Initial Training | • Trained the model using vectorized text features. • Evaluated initial performance using accuracy metrics. | None
28th November 2025 | 10 | Advanced Model Implementation | • Implemented a second classification model (Logistic Regression). • Tuned basic hyperparameters to improve performance. • Compared preliminary results with the baseline model. | Minor code issues.
2nd December 2025 | 11 | Model Evaluation | • Evaluated both models using precision, recall, F1-score, and confusion matrix. • Visualized performance metrics for comparison. | Minor code issues.
10th December 2025 | 12 | Results Analysis & Interpretation | • Analyzed evaluation results and compared model performances. | No major issues encountered.
19th December 2025 | 13 | Documentation & Report Writing | • Added screenshots, tables, and explanations as required. • Ensured alignment with marking criteria. | Managing report length while keeping explanations concise.
26th December 2025 | 14 | Final Review for Submission | • Cleaned and organized Notebook code. • Ensure meeting all the requirments. | None
7th January 2026 | 16 | Project Submission | • Prepared GitHub repository with code and dataset. • Created final ZIP file for Moodle submission. | None